## General
Branch | Task | Member | Days for execution | Time period
Organisational | Shared drive | Dinko | 2 | 15-Sept - 17-Sept
| Shared GitHub | Boris | 2 | 15-Sept - 17-Sept
| Docker installation | everyone | 2 | 15-Sept - 17-Sept
| Jira set up | Aneliya | 2 | 15-Sept - 17-Sept
Documentations | Test Plan creation | everyone |  | 18-Sept - ongoing
| Test scenarios/overview | Dinko | 4 | 15-Sept-18-Sept
| Test cases creation | everyone | 10 | 18-Sept-28-Sept
Reporting
Testing | Exploratory testing | everyone | 3 | 18-Sept-20-Sept
| Manual testing | everyone | 9 | 20-Sept-28-Sept
Automation testing:
| *UI testing | everyone | 7 | 22-Sept-29-Sept
| *Postman | everyone | 7 | 29-Sept-6-Oct
| *Rest Assured | everyone | 11 | 29-Sept-10-Oct
Re-testing | Smoke testing | everyone |  | 10-Oct-20-Oct
Optional | *non-functional testing | everyone |  | 10-Oct-20-Oct

## UI testing
User Role | Test scenarios | Member | Progress
Non-registered users | Login | Boris | Done
| Registration | Aneliya | Done
| Search posts and profiles | Aneliya | Done
Registered User | Edit profile info | Boris | Done
| Create post | Dinko | Done
| Comment a post | Dinko | Done
| Update post | Dinko | Done
| Delete post | Dinko | Done
| Like a post | Dinko | Done
| Unlike post | Dinko | Done
| Like a comment | Dinko | Done
| Unlike comment | Dinko | Done
| Get newest posts | Aneliya | Done
| Search | Aneliya | Done
| Connect to user | Boris | Done
| Disconnect | Boris | Done
Admin | Disable profile | Boris | Done
| Enable profile | Boris | Done
| Edit a post | Aneliya | Done
| Delete a post | Aneliya | Done
| Edit a comment | Aneliya | Done
| Delete comment | Aneliya | Done

## Postman&Rest Assured
API - controllers | API-tests | Postman | Member | Rest Assured | Memmber
comment-controllers | /api/comment findAll | Ready | Aneliya | Ready | Boris
| /api/comment/auth/creator save | Ready | Aneliya | Ready | Boris
| /api/comment/auth/editor editComment | Ready | Aneliya | Ready | Boris
| /api/comment/auth/likesUp likeComment | Ready | Aneliya | Ready | Boris
| /api/comment/auth/manager deleteComment | Ready | Aneliya | Ready | Boris
| /api/comment/byPost findAllCommentsOfPost | Ready | Aneliya | Ready | Boris
| /api/comment/single getOne | Ready | Aneliya | Ready | Boris
connection-contollers | /api/auth/requestsendRequest | Ready | Dinko | Ready | Aneliya
| /api/auth/users/{id}/request/ getUserRequests | Ready | Dinko | Ready | Aneliya
| /api/auth/users/{id}/request/approve approveRequests | Ready | Dinko | Ready | Aneliya
post-controllers | /api/post/ findAll | Ready | Aneliya | Ready | Boris
| /api/post/auth/creator save | Ready | Aneliya | Ready | Boris
| /api/post/auth/editor editPost | Ready | Aneliya | Ready | Boris
| /api/post/auth/likesUp likeAPost | Ready | Aneliya | Ready | Boris
| /api/post/auth/manager deletePost | Ready | Aneliya | Ready | Boris
| /api/post/Comments showComments | Ready | Aneliya | Ready | Boris
skill-contollers | /api/skill findAll | Ready | Boris | Ready | Aneliya
| /api/skill/create save | Ready | Boris | Ready | Aneliya
| /api/skill/delete deleteSkill | Ready | Boris | Ready | Aneliya
| /api/skill/edit editSkill | Ready | Boris | Ready | Aneliya
| /api/skill/getOne getOne | Ready | Boris | Ready | Aneliya
user-controllers | /api/users getUsers | Ready | Aneliya | Ready | Boris
| /api/users/registerUser | Ready | Aneliya | Ready | Boris
| /api/users/{id}/posts showProfilePosts | Ready | Boris | Ready | Boris
| /api/users/auth/{id} getUserById | Ready | Boris | Ready | Boris
| /api/users/auth/{id}/expertise upgradeUserExpertiseProfile | Ready | Aneliya | Ready | Boris
| /api/users/auth/{id}/personal upgradeUserPersonalProfile | Ready | Aneliya | Ready | Boris
Happy path | Registration, Login, Create & edit post, Create & edit comment, Delete | Ready | Aneliya
Total | 28

## App functional reqirements (hidden)
entities | username | unique | 2-20 symbols | must
| password | capital letter and special symbol | 8-~ symbols | must
| emial | unique | valid? | must
public part | register |  |  | must
anonymous user | login |  |  | must
| public feed | chronologically |  | must
| profile search | based on name/email |  | must
private part | login |  |  | must
| update info | name, pic, visibility |  | must
| change pass/email |  |  | optional
| request connect |  |  | must
| request disconnect |  |  | must